LAND USE APPLICATION – LETTER OF INTENT

From:		Legacy Custom Remodeling, LLC

Josh Wanta, Owner

7602 Riverside Road

Verona, WI  53593

josh@legacycr.com

Phone:  608-835-1822

Architect:	Ryan Schultz

OpenDesign.com

316 West Washington Ave., Suite 675

Madison, WI  53703

Ryan.Schultz@opendesign.com

Phone:  773-425-6456

Re:		Letter of Intent for Garage and Accessory Dwelling Unit (ADU)

1020 Sherman Avenue, Madison, WI  53703

Owners:  Mike and Maura Crooks

mcrooks@vonbriesen.com

Phone:  608-287-3926

Date:		April 8, 2018

Project Team

- Josh Wanta, owner of Legacy Custom Remodeling will general contract the construction of this 15 x 30 two story, garage and residential dwelling accessory unit in rear of home

- Subcontractors and material suppliers as coordinated by general contractor

Existing Conditions

- Residential home with large backyard

- No existing structures/buildings will be changed

- Construction access to rear yard will be on north side of home, same side as home’s driveway and prior garage

Project Schedule

- June 23rd – Plan Commission meeting and approval of ADU

- June 24th – zoning, building permits, parks fee, prep site for access, utility connections

- June 26th – excavate and pour foundation

- September 1st – complete building, restore landscape/lawn

Proposed Uses

- Garage for owner occupied residence

- This ADU is planned to be used by the owner’s family (four children and seven siblings) when visiting

- The ADU is 700 square feet of conditioned space and 25 square feet of open front porch

Hours of Operation of Construction

- Monday-Friday, 7:30 a.m. to 5:00 p.m.

- Saturday, 8:00 a.m. to 5:00 p.m.

Building Square Footage

- Total size of building is 700 square feet of building footprint

Number of Dwelling Units

- After project is completed, this lot will have one primary dwelling unit, plus one garage and one accessory dwelling unit (total of 2 dwelling units) above the garage

Auto Parking

- The garage will open up two spots on Sherman Avenue where parking is at a premium

Lot Coverage and Usable Open Space Calculation

- Existing home = 3,500 square feet

- Existing driveway, front porch and back patio = 1,000 square feet

- Proposed ADU = 700 square feet

- 1020 Sherman Avenue lot parcel – 9,000 square feet

- Remaining useable/open AFTER completing proposed ADU = 6,000 square feet which is 70% green space

Value of Land (existing)

- Land Value			$500,000.00

- Improved Value		$300,000.00

- Total Value			$800,000.00

Estimated Project Cost

- Estimated costs to building proposed garage and ADU is $150,000.00

Number of Construction and Full-Time Equivalent Jobs Created

- Estimated 4 full time equivalent jobs created for 9 weeks

Public Subsidy Requested

- No public subsidy is being requested

Exterior Finish of ADU

- Exterior finish shall be similar to existing primary dwelling including vinyl siding, aluminum soffit/fascia, 5/12 pitch hip roof with 20” overhangs, vinyl double hung windows

Others Contacted

- Alder

  - Aldermanic District: 2

  - Ald. Ledell Zellers

  - district2@cityofmadison.com

- Neighborhood Association

- Tenney-Lapham Neighborhood Association

- https://www.cityofmadison.com/neighborhoods/profile/92.html

- Patty Prime, pprime@gmail.com

- Tyler Lark, tylerlark@gmail.com

We will notify them again 30 days before we submit our application.